|  | # Annual Utah Behavioral Health Commission Report State of Utah Utah Behavioral Health Commission [Date] |
| --- | --- |

To:	Utah State Legislature: Health and Human Services Interim Committee, Social Services Appropriations Subcommittee, President Adams, and Speaker Schultz

From:	Ally Isom, Chairperson, Utah Behavioral Health Commission

Subject: 	Annual Report

# Purpose

As required by 26B-5-703, the Utah Behavioral Health Commission submits this report to the Legislature that includes:

- recommendations for behavioral health measures and targets to be included in the next update to the master plan;

- recommendations for consolidating into the commission other commissions, committees, subcommittees, task forces, working groups, or other bodies pertaining to behavioral health;

- recommendations on the next steps for reviewing and potentially redefining state law and program options regarding county-based behavioral health services; and

- recommendations on key budget priorities and key legislative policies for the 2025 General Session and thereafter.

Executive Summary

Senate Bill 27 (2024) consolidated several committees to create the Utah Behavioral Health Commission (Commission).  Senate Bill 27 also directed the Commission to report on four areas by December 31, 2024.  The Commission met eight times from July to December 2024 to consider each of these areas.  Because of the short time frame, in some cases, the Commission has not yet adopted specific recommendations but instead has outlined a process for how it will do so in 2025.  A key priority of the Commission in 2025 will be to convert the current Behavioral Health Assessment & Master Plan (Master Plan) into a strategic plan.  The strategic plan will then guide the Commission as it addresses these areas.

The Commission reports the following for these areas:

Behavioral health measures and targets

The Commission reviewed an inventory of existing measures and targets.  In 2025, the Commission will use the strategic planning process to identify appropriate measures and targets to monitor whether or not the state is achieving the behavioral health outcomes it is seeking.

Consolidating committees

The Commission organized its subcommittee structure  and reviewed an inventory of existing committees.  In 2025, the Commission will use the strategic planning process to organize its subcommittees and determine if any other existing committees should be consolidated within the Commission.

County-based behavioral health services

The Commission recommends the addition of the behavioral health matching funds to the Medicaid consensus process.  The Commission recommends that the Office of Substance Use and Mental Health (OSUMH) present its annual reports on the local authorities’ use of funds to their respective governing bodies.  In 2025 and 2026, the Commission will continue to collect information related to the statutory roles and responsibilities of the local authorities and make recommendations to the Legislature about potential ways to improve the responsibilities and funding of county-based behavioral health services.

Budget priorities and legislative policies

The Commission adopted a list of budget priorities and legislative policies outlined in the corresponding section of this report.  In 2025, the Commission will use the strategic plan it will develop to provide additional guidance about the budget priorities and legislative policies it will recommend to the Legislature.

# Primary report

Through Senate Bill 27, Behavioral Health System Amendments, sponsored by Senator Evan Vickers, and Representative Steve Eliason in the 2024 General Session, the Utah State Legislature created the Utah Behavioral Health Commission (Commission).  Statute designates the Commission as the central authority for coordinating behavioral health initiatives between state and local governments, health systems, and other interested persons, to ensure that Utah’s behavioral health systems are comprehensive, aligned, effective, and efficient.  As designated in statute, the Department of Health and Human Services (DHHS), Office of Substance Use and Mental Health (OSUMH) provides staff support to the Commission.

This eleven-member Commission started meeting in July 2024.  The chart below identifies the members of the commission:

| Name | Title | Seat |
| --- | --- | --- |
| Evan Done | Associate Director, Utah Support Advocates for Recovery Awareness | Representative with lived experience with substance use disorder |
| Julie Henderson Hardle | Retired Recovery and Resiliency Manager at Optum/United Healthcare | Representative with lived experience with mental health |
| Ally Isom | Chief Strategy & Marketing Officer, Clyde Companies | Family representative |
| Tracy Gruber JD | Executive Director, Utah Department of Health and Human Services | State behavioral health system representative |
| Tammer Attallah MBA, LCSW | Executive Clinical Director, Intermountain Healthcare | Major healthcare systems representative |
| Jordan Sorenson MHA | Director Behavioral Health Policy and Emergency Preparedness, Utah Hospital Association | Private acute care representative |
| Adam Cohen MBA | President & Chief Executive Officer, Odyssey House of Utah | Private outpatient representative |
| Mike Deal MPA | Executive Director, Southwest Behavioral Health Center | Utah Behavioral Health Committee of the Utah Association of Counties representative |
| Kyle Snow MBA | Corporate Executive Officer, Northeastern Counseling Center | Rural communities representative |
| James Ashworth MD | Associate Professor (Clinical) | Large employers representative |
| Elaine Navar LCSW | Licensed Clinical Social Work Therapist | Historically underrepresented populations representative |

In addition, Senate Bill 27 realigned four existing statutory commissions, committees or councils that now function as committees or subcommittees of the newly formed Commission.  The impacted entities are listed below:

- Behavioral Health Crisis Response Committee: Conducts studies and makes recommendations for behavioral health crisis needs in Utah, including crisis line practice and needs, the operation of the statewide 988 hotline, and standards for statewide mobile crisis outreach teams.

- Statewide Suicide Prevention Committee and Coalition: Gathers, monitors, and analyzes trends, data, research, and systems to identify prevention, intervention, and postvention needs and develop a statewide plan to reduce suicidal behaviors and promote life quality equitably.

- Utah Substance Use and Mental Health Advisory Committee (USAAV+): Recommends and coordinates the creation, dissemination, and implementation of statewide policies to address substance use and mental health disorders.

- Education and Mental Health Council provides action-oriented guidance to legislative and other state leaders on how to meet the behavioral health needs, including mental health and substance use issues, facing youth and families within the state; and ensure close collaboration and alignment with existing statewide behavioral health efforts and groups.  The Education and Mental Health Council will sunset on December 31, 2024.

This report includes recommendations made by the subcommittees and endorsed by the Commission.  Each of the four areas identified in statute will be addressed in separate sections of the report.

Behavioral health measures and targets

# Requirement:

# (a) recommendations for behavioral health measures and targets to be included in the next update to the master plan;

The release of the Utah Behavioral Health Assessment & Master Plan (Master Plan) in January 2024 identified potential steps for future reform.  The Master Plan identifies more than 200 specific recommendations for the behavioral health system in Utah.  However, additional work needs to be completed to further refine this plan.  As noted by a recent legislative audit of the governance of Utah’s behavioral health system, additional prioritization is needed to make the Master Plan actionable.  The Master Plan does not identify targets and the roles of various stakeholders in the implementation process.  Finally, the Commission needs to identify measures to inform and improve policy development, adoption, implementation, and effectiveness, and build the evidence base for further policy interventions.

The recent legislative audit of Utah behavioral health system identified:

“Strategic plans are the starting point and basic underpinning for a system of program goal setting and performance measurement .  .  .  A multi-year strategic plan articulates the fundamental mission (or missions) of an organization, and lays out its long-term general goals for implementing that mission, including the resources needed to reach these goals.”

## The Commission will work to create a strategic plan for Utah building on the Master Plan, which will include the measures and targets required by 26B-5-703.  Specifically, the Commission will work to address several issues raised in the Master Plan:

## Evaluate outcome measures and support system-wide adoption of evidence-based practices and a standardized set of quality measures

## Increase the use of valid measures that provide transparency into outcomes

## Activities Accomplished in 2024

The Commission has formally adopted the mission and guiding principles of the Master Plan.  Based on this mission and guiding principles, the Commission developed a scoresheet to use in assessing policy and budget recommendations for 2024.

OSUMH has completed an inventory of the metrics currently used in the public behavioral health system.  The inventory is included in this report as Appendix A.  In addition, OSUMH has developed its strategic plan that includes measures and targets for itself and the state (see Appendix B).

## Next Steps for 2025

The Commission did not develop recommendations for measures and targets in 2024, because its members determined that these should be determined through a careful and intentional strategic planning process that will take additional time.  The planned process for the strategic plan in 2025 is described below.

In 2025, the Commission will refine the Master Plan into a five-year strategic plan with measures and targets.  OSUMH staff will support the Commission in 2025 to develop a strategic plan in a similar format to OSUMH’s strategic plan.

The final strategic plan will include:

- Strategies (Example: Advance prevention and early intervention to reduce the impact of substance use and mental health disorders, substance misuse, and to promote well-being);

- Objectives for each strategy (Example: Reduce deaths due to drug overdose);

- Associated indicators/performance measures (Example: Utah drug overdose deaths);

- Secondary measures (Example: Naloxone kits distributed, numbers served);

- Tactics for achieving objectives (Example: Continue to partner with and provide funding to statewide organizations that train and distribute Naloxone kits with the goal of increasing annual distribution by 5%.  45,342 kits were provided in FY24, goal for FY25 is 47,609);

- Assigned responsible units and leaders; and

- A specific outline for monitoring objectives.

The development process will involve the following phases:

| Time Period | Process | Associated Outputs |
| --- | --- | --- |
| January - February 2025 | Build on the strategic priorities of the Master Plan to develop the strategies for the Commission’s behavioral health strategic plan. | - Strategies of the strategic plan |
| March - June 2025 | Engage with national and private organizations to discuss meaningful measures of behavioral health service quality. | - Meetings with national and private organizations - Overview of relevant literature |
|  | Develop objectives, performance measures, and tactics to support these strategies. Each strategy will have multiple objectives, and performance measures include specific targets or indicators that the Commission aims to achieve. | - Objectives - Performance measures - Tactics |
|  | Determine gaps in public and private data that may act as barriers to measuring objectives, and integrate ways to address these gaps into other sections of the strategic plan. | - Overview of gaps in public and private data |
| July 2025 | Assign responsible units and leaders to each objective. | - Assignments for objectives |
| August - September 2025 | Develop a draft five-year strategic plan. Appendix B includes an example of a strategic plan developed by OSUMH. | - Draft strategic plan |
| October 2025 | Solicit input from stakeholders on the draft strategic plan. | - Overview of stakeholder input |
| November - December 2025 | Finalize the strategic plan and prepare for monitoring and execution that will begin in January 2026. | - Final strategic plan |
| 2026 and beyond | Execute and monitor implementation of the strategic plan. | - Tracking document on strategic plan. - Regular updates on strategic plan implementation during meetings. |

The strategic plan will cover calendar years 2026 - 2030.  While strategies may remain the same over these five years, the Commission will regularly revisit its objectives, performance measures, and tactics to ensure they are supporting its goals.  Tactics will have shorter timeframes, such as one year, for execution.  These tactics will be part of an annual work plan that will be included in the strategic plan.

Consolidating committees

# Requirement:

# (b) recommendations for consolidating into the Commission other commissions, committees, subcommittees, task forces, working groups, or other bodies pertaining to behavioral health;

## 2024 Accomplishments

The diagram below shows the current structure of the Commission’s subcommittees.

In 2024, the Commission’s subcommittees presented on their history, mission, and activities during Commission meetings.  This process educated Commission members on the current subcommittee structure.  Subcommittees also presented budget and policy recommendations at several Commission meetings.  In addition, the Commission’s staff convened members of the subcommittees to discuss their current structure, how they coordinate with each other and the Commission, and how they would recommend reenvisioning and consolidating these subcommittees.

The Commission then conducted an initial analysis of its subcommittee structure and how the purpose and activities of each subcommittee aligns with the strategic priorities of the Master Plan.

The Commission identified several potential gaps in its structure:

- Children and youth: Many recommendations in the Master Plan specifically target children, youth, and families.  The current subcommittee structure has several groups that address children and youth, but not comprehensively across substance use and mental issues from ages 0 through 26.  These subcommittees are:

  - Utah Prevention Advisory Committee: Only focuses on prevention activities, and not recovery or treatment.

  - Underage Drinking Prevention Workgroup: Only focuses on underage drinking and prevention.

  - Statewide Suicide Prevention Commitee and Coalition: Only focuses on suicide prevention.

  - Drug Endangered Children Committee: Not actively meeting, only focuses on punitive policies for offenders that endanger children.

- Data and evaluation: The Commission does not have any subcommittees that explicitly focus on any items regarding data and evaluation.  Potential activities include:

  - Developing system-wide data collaboration;

  - Identifying meaningful, validated metrics at the population, plan, and provider level; and

  - Promoting the use of validated, meaningful outcome tools that can be used by behavioral health providers.

- Integrating behavioral and physical health care: The Commission does not have any subcommittees that regularly focus on the integration of behavioral and physical health care.  The Commission may be able to consolidate existing subcommittees to ensure at least one subcommittee explicitly focuses on this issue, which is a strategic priority of the Master Plan.

To ensure the Commission has an efficient structure and avoid the creation of additional subcommittees, the Commission will consider options for addressing these gaps when it completes the process outlined below for 2025 and restructures its subcommittees.  The Commission has decided to wait until the completion of its strategic plan before proposing any restructuring or consolidation of related committees, to ensure that the final restructuring and consolidation fully meets the needs of the Commission’s objectives.

## Next Steps for 2025

In 2025, the Commission will continue to review its subcommittee structure, and also consider its intersection with other behavioral health-related groups.  The Commission will solicit input from subcommittees, other related commissions, other related task forces, etc.  on their goals, regular activities, membership, and purpose.

| Time Period | Process | Associated Outputs |
| --- | --- | --- |
| January - May 2025 | Solicit input from subcommittees on potential opportunities for consolidation and integration in the current committee structure. | - Subcommittee chairs present at Commission meetings |
|  | Engage with the following committees and groups to discuss opportunities for consolidation and coordination: - Alcohol Abuse Tracking Committee - Fentanyl Task Force - Health Workforce Advisory Council - Opioid Community Collaborative Meetings - Opioid Task Force - Utah Community Health Advisory Board - Utah Hospital Association Behavioral Health Committee - Utah Tobacco Free Alliance - Youth Electronic, Marijuana, and Other Drugs Prevention Committee | - Presentations at Commission meetings - Requests for information via email |
| June - July 2025 | Assess areas of duplication within the behavioral health committee structure and consider potential gaps. The Commission will use its draft strategic plan to guide this analysis and determine whether the committee structure aligns with the priorities and outcomes of this strategic plan. | - Analysis of gaps and duplication within committee structure |
| August 2025 | Propose options for restructuring subcommittees of the Commission and other existing workgroups, committees, etc. that focus on behavioral health. The Commission will eliminate or consolidate groups where it has identified areas of duplication, and propose the creation or consolidation of groups where it has identified gaps. | - Proposal for restructuring committees - Public comment opportunities at Commission meeting |
| September 2025 | Adjust options as appropriate based on feedback, and submit a final set of recommendations for consolidation in the legislative report due on September 30, 2025. | - Final recommendations for restructuring committees |

To ensure subcommittees’ independence from DHHS, OSUMH determined that its staff would no longer chair any of these subcommittees.  However, in 2025 and beyond, DHHS employees will continue acting as supporting staff to these subcommittees.

# County-based behavioral health services

# Request:

# (c) recommendations on the next steps for reviewing and potentially redefining state law and program options regarding county-based behavioral health services; and

Redefining state law and program options regarding county-based behavioral health services would be a significant change in the delivery of behavioral health services in Utah.  The Commission plans to review options for potential changes in this system through a careful, systematic, and incremental process to ensure any potential recommendations have a positive impact on access, alignment of systems, equity, and value.

## 2024 Accomplishments and Recommendations

1.  In November 2024, the Commission received a recommendation from USAAV+, a subcommittee of the Commission, related to improving state processes for county behavioral health services.  USAAV+ recommended that the state update the Medicaid consensus process to include the state general fund appropriation for county behavioral health services that is currently used for  Medicaid match in this process:

- Each year, executive and legislative agencies complete the Medicaid consensus process to determine state Medicaid funding for certain physical and behavioral health services.  Consensus funding for physical health services considers multiple factors, including population growth, changes in the federal match rate (the Federal Medical Assistance Percentage, or FMAP), and certain provider increases.  State consensus funding on the behavioral health side does not include changes in the federal match rate or caseload in its consensus process.  This exclusion has posed a challenge for counties.  Counties provide behavioral health services in Utah, and as the federal match rate has decreased over time and enrollment has increased, the county spending on behavioral health services has increased.

- In addition, Utah statute generally directs counties to provide a 20% county match for state funding given to the counties by OSUMH.  As the federal match rate has fluctuated for behavioral health services and state match has not increased, counties have been paying more than 20% of the funding for behavioral health services, and statewide, counties currently fund about 30% of these expenditures, which has further strained county budgets.

- USAAV+ consequently recommended that Utah’s executive and legislative agencies update the Medicaid consensus process to include the federal match rate and enrollment in calculating consensus funding for county behavioral health services.  This would not necessarily require changes in statute, but could occur within the existing process completed by executive and legislative agencies.

The commission voted: [insert commission vote]

2.  The recent performance audit on the governance of Utah’s behavioral health system recommended that OSUMH engage with local authorities to directly address issues associated with noncompliance.

To support OSUMH in this engagement, the Commission has recommended that OSUMH improve communication and enhance transparency of annual audit findings, including annual in-person review of audit findings with local county authority boards and elected officials regarding audit results, and specifically with noncompliance issues.  These presentations will include audit findings, steps taken to address non-compliance, and a chart in the audit report that identifies all funds allocated to the local authority  that are unspent, transferred to another local authority, or withheld by OSUMH.  OSUMH will publicly post all audit reports.

## Next Steps for 2025

In 2025, the Commission will dedicate a portion of its agendas to reviewing state law and program options for county-based behavioral health services.

| Time Period | Process | Associated Outputs |
| --- | --- | --- |
| January - December 2025 | Solicit input from key stakeholders on the strengths, gaps, and opportunities for improvement in the current county behavioral health system, and how state law impacts that system. | - Meetings with stakeholders - Subcommittee presentations - Letters and reports from interested stakeholders |
|  | Review data on outcomes in the county behavioral health system to improve the quality of this system. | - Data analyses - Findings on gaps on data |
| January - June 2026 | Develop policy options for improving the county behavioral health system that support the state in reaching the objectives and performance measures identified in its strategic plan | - Policy report to the Legislature in 2026 |
| July 2026 and onward | Track the impact of any implemented changes through stakeholder engagement and its ongoing review of the strategic plan. | - Monitoring system through the strategic plan |

# Budget priorities and legislative policies

# Requirement:

# (d) recommendations on key budget priorities and key legislative policies for the 2025 General Session and thereafter.

## 2024 Accomplishments and Recommendations for 2025 General Session

The Commission received policy and budget recommendations from its subcommittees and several Commission members.  The Commission required subcommittees to complete a template form for each recommendation (included as Appendix C), and evaluated each proposal using a scorecard built around the mission and guiding principles of the Master Plan (Appendix D).

## Policy and Budget Recommendation Process for 2025 and Beyond

2025 General Session

On January 28, 2025, the Commission will develop a Revised Prioritization Recommendations List for the 2025 General Session that includes ongoing recommendations that Commission members receive from legislators, key stakeholders, and its subcommittees, and submit these recommendations to the 2025 Legislature.  This list will allow the Commission to provide input on recommendations that were not received within the required timeframe for 2024, when the process for recommendations review was new to its members, legislators, and subcommittees.

[This section will be completed after the Commission votes on its policy and budget recommendations during the December 5, 2024 meeting.]

## USAAV+ and Legislative Analysis

USAAV+, a subcommittee of the Commission, is required in statute to analyze and provide an objective assessment of all proposed legislation concerning substance use, mental health, forensic mental health, and related issues.  USAAV+ will follow the process listed below during the 2025 General Session, which is similar to its approach in previous years:

- USAAV+ meets weekly during the General Session to review bills that its staff flag as impacting behavioral health.

  - USAAV+ members may attend and vote in person or virtually.

- USAAV+ will prioritize reviewing bills that directly relate to the priorities of the Master Plan.

- During each meeting, USAAV+ discusses all flagged bills and votes to take positions on all bills.

  - Bill positions

    - Support: Support the bill

    - Support in Concept: Support, but there’s an area of concern

    - Oppose: Opposition to the bill (requires an opposition statement)

    - No position: Neutral

    - Hold: Hold the bill for further information

    - Priority support: Priority for passage (requires a position statement)

    - Beyond scope: Not within the scope of USAAV+

- USAAV+’s membership includes executive agency staff.

  - USAAV+ members who are executive agency staff will continue to abstain from voting on any bill that the Governor’s budget does not explicitly endorse or support.

- Anyone with expertise may describe or present a bill to USAAV+

  - USAAV+ members can discuss each bill in advance of the vote.

  - Members of the public have an opportunity to comment in advance of a vote.

USAAV+ will engage directly with the Commission as follows:

- USAAV+ will include Commission members in the weekly email on bills that USAAV+ is tracking.

- USAAV+ will email Commission members to flag any bills that:

  - USAAV+ deems as high priority for Commission members to review.

  - Explicitly impact the Commission (e.g., change the membership of the Commission).

- USAAV+ will invite Commission members to attend all weekly meetings.

  - Commission members may comment on bills as members of the public during weekly meetings.

  - Commission members may also communicate their input on bills via email to SUMH staff.

2025 Interim Session and Beyond

The Commission will update its scoresheet and recommendation form in 2025, informed by the strategies and objectives listed in its strategic plan.  The Commission will share these updated documents with its subcommittees in March 2025, and require that subcommittees present at Commission meetings and submit their forms by June 30, 2025.  The Commission will finalize its prioritized policy recommendations for the Legislative Policy Committee by August 31, 2025.

The Commission will provide a report to the Health and Human Services Interim Committee by September 30, 2025, that describes the Commission's work during the preceding year and includes any legislative recommendations from the Commission.

Appendix A:

Outcome Measures used in Public Behavioral Health

Population Outcome Measures

- Utah drug overdose deaths per 100,000 population (data source-IBIS)

- Utah suicide deaths per 100,000 population (data source-IBIS)

- Percentage of Utah adults reporting poor mental health (data source-IBIS)

- Percentage of Utah youth in need of alcohol or drug treatment (data source-SHARP)

- Percentage of Utah youth with high mental health treatment needs (data source-SHARP)

- Equitable access: All communities receive mental health services proportionate to their level of need

Plan Outcome Measures (HEDIS Core Measures)

- Follow-Up Care for Children Prescribed ADHD Medication (ADD-E)

- Antidepressant Medication Management (AMM)

- Metabolic Monitoring for Children and Adolescents on Antipsychotics (APM-E)

- Use of First-Line Psychosocial Care for Children and Adolescents on Antipsychotics (APP)

- Follow-Up After Emergency Department Visit for Substance Use Disorder (FUA)

- Follow-Up After Hospitalization for Mental Illness (FUH)

- Follow-Up After High-Intensity Care for Substance Use Disorder (FUI)

- Follow-Up After Emergency Department Visit for Mental Illness (FUM)

- Initiation and Engagement of Substance Use Disorder Treatment (IET)

- Adherence to Antipsychotic Medications for Individuals with Schizophrenia (SAA)

- Diabetes Screening for People with Schizophrenia or Bipolar Disorder Who Are Using Antipsychotic Medications (SSD)

- Cardiovascular Monitoring for People with Cardiovascular Disease and Schizophrenia (SMC)

- Diabetes Monitoring for People with Diabetes and Schizophrenia (SMD)

Provider Outcome Measures

- Improvement in client mental health status

  - Measures

    - Mental Health Statistics Improvement Program(MHSIP) Client satisfaction survey (annual)

    - Outcome Questionnaire (OQ) Analyst- MH clients (not more than once every 7 days)

    - Substance Use Recovery Evaluator (SURE) - SUD clients

    - TEDS (Treatment Episode Data Set)  involvement in Social Support Groups.  Increase attendance from Admission to Discharge

- Increases in client participation in employment, education and meaningful activities

  - Measures

    - Employment status collected in MH event level data and at admission and discharge in SUD as part of the TEDS NOMS (National Outcomes Measures) increase in employment from admission to discharge

    - Enrolled in school is collected in MH event level data

- Reduced client involvement in criminal justice systems and increased access for treatment for forensic patients

  - Measures

    - TEDS NOMS decreased number of arrests from admission to discharge

- Reduced avoidable use of hospital, emergency rooms and crisis services

  - Measures

    - Collect perception of alternative and law enforcement involvement for Receiving Center, MCOT (Mobile Crisis Outreach Team), and SMR (Stabilization and Mobile Response) clients

    - Emergency indicator collected on all mental health events

- Increased housing stability in the community

  - Measures

    - Mental Health and SUD Living Arrangements.  Collected at admission for MH and at admission and discharge for SUD.  Part of the TEDS NOMS - increased housing stability from admission to discharge.

- Improved client satisfaction with quality of life

  - Measures

    - The Mental Health Statistics Improvement Program (MHSIP) is a behavioral health client survey.  The MHSIP measures client opinion of their treatment services.  The MHSIP is used by most states to meet Federal mental health dollars.  Utah administers the MHSIP each year through the Utah County-based local mental health and substance use disorder treatment system.

    - MHSIP Scorecard for Utah

- Decreased population level disparities in access to treatment and treatment outcomes

  - Measures

    - National MHSIP consumer satisfaction survey stratifies responses by race and ethnicity

    - Most data can be identified by different demographic groups

Grant Outcomes:

  - Measures

    - The NOMs (National Outcomes Measurement System) and GPRA (Government Performance and Results Act) collects all the above outcome measures (mental health status, employment, education, housing, etc.).  There is client level data and programmatic data.

# Appendix B: OSUMH Strategic Plan

Formatting will be adjusted in final version

DHHS-DIH_SUMH RBA  SFY25

Appendix C

Recommendation Form for

Subcommittees of the Utah Behavioral Health Commission

Instructions: Subcommittees of the Utah Behavioral Health Commission should fill out a separate form for each separate policy or budget recommendation.

Summary

- Title: - Subcommittee: - Description of recommendation (limited to approximately 200 words):

Legislation and Cost

- Budget implications of recommendation, if any: - Does this recommendation require changes to statute? If yes, please provide an attachment with citations and provide recommended statutory changes.

Alignment with the Utah Behavioral Health Master Plan

- Describe how this recommendation addresses the mission of the Utah Behavioral Health Master Plan (limited to approximately 200 words): - Describe how this recommendation is consistent with each of the guiding principles of the Utah Behavioral Health Master Plan (limited to approximately 300 words):

Outcomes and Measurement

- What outcomes does this recommendation aim to achieve, and how will these outcomes be measured?

# Appendix D

# Scoresheet

| Utah Behavioral Health Commission Scoresheet |  |  |
| --- | --- | --- |
| Utah Code 26B-5-703 (1) The purpose of the commission is to be the central authority for coordinating behavioral health initiatives between state and local governments, health systems, and other interested persons, to ensure that Utah's behavioral health systems are comprehensive, aligned, effective, and efficient. |  |  |
| The project is aligned with the Master Plan's mission | Points Possible | Awarded |
| Create equitable, aligned, and effective behavioral health systems that provide timely access to person-centered and culturally responsive care to all Utahns through a comprehensive continuum of behavioral health services and supports. | 15 |  |
| The project is consistent with the Master Plan's guiding principles |  |  |
| Access: Reforms should increase access to person-centered, prompt, and affordable behavioral health services and supports to all Utahns across the population lifespan. | 10 |  |
| Alignment: Reforms should support coordinated, navigable, and sustainable behavioral health services across public and private systems, payers, and sectors. | 10 |  |
| Equity: Reforms should address behavioral health disparities and promote a state in which everyone has a fair and just opportunity to attain their highest level of health. | 5 |  |
| Value: Reforms should encourage investments in effective behavioral health services that demonstrate both direct savings and indirect medical, educational, and social service savings. | 5 |  |
| Total: | 45 | 0 |
| The project is aligned with the Master Plan's strategic priorities | Yes or no |  |
| (I) Support continued use, implementation, creation, and innovation of evidence-based interventions. |  |  |
| (II) Strengthen behavioral health prevention and early intervention. |  |  |
| (III) Integrate physical and behavioral health. |  |  |
| (IV) Improve patient, family, and consumer navigation. |  |  |
| (V) Continue to build out Utah’s behavioral health crisis and stabilization systems. |  |  |
| (VI) Improve the availability of services and supports for individuals with serious mental illness and complex behavioral health needs and their families. |  |  |
| (VII) Expand, support, and diversify Utah’s behavioral health workforce. |  |  |