Utah Broadband Advisory Commission 2025

Utah Broadband Advisory Commission Meeting Minutes

Tuesday, June 13 ⋅11:00am – 12:00pm

Virtual Meeting

Attendees:

- Members Attending Virtually: Senator Chris Wilson (Co-chair), Representative Scott Chew (Co-chair), Senator Harper, Rebecca Dilg (non-voting member), Chris Parker, Lynne Yocom, Kelleigh Cole, Laura Hanson (appointed stand-in for Sophia DiCaro) and Representative Paul Cutler.

- Online Staff: Samantha Tiburcio-Escalante, Elizabeth Henrikson, Steve Greene, Lindsey Thurgood, Kenrick Gordon, Todd Jensen, Sara Edgar, Robert Busch and Kamron Dalton.

- Online Visitors: Cynthia Olsen, Kira Slawson, Ivan Hartle, Mujtaba “Moosh” Ansari, Sylvia Wilkins, Rachel Boe, Robert Spendlove, and Jodi Hart Wilson.

1. Welcome and Introduction

- The meeting was called to order by Senator Chris Wilson. Representative Chew welcomed everyone to the June 13, 2025, Broadband Advisory Commission virtual meeting.

2. Approval of Previous Meeting Minutes

- Representative Scott Chew called for a motion to approve the minutes from December 13, 2024.

- Senator Chris Wilson made a motion to approve the minutes. The motion passed unanimously. No nay votes were recorded.

- A round of introductions followed, where each participant stated their name, affiliation, and role.

3. Broadband Access Update (Steve Greene, Utah Broadband Center)

- Steve Greene provided an update on the Capital Project Funds (CPF) broadband access grant program, which is part of the ARPA grant.

- Funding Allocation: Out of $15 million in capital project funds, $14,780,810 has been allocated to 7 projects across the State.

- Fiber Installation: To date, 146.73 miles of fiber have been installed. This is new fiber that extends existing "middle mile" fiber into communities as "last mile" fiber, and it is currently connected and live.

- Homes Passed: 2,100 homes have been "passed" (meaning they can be served within 10 days, as per federal definition). The project aims to pass a total of 3,200 homes by its conclusion.

- Project Completion Status:

  - All West completed its project in Croydon.

  - Direct Communications completed its fiber project in White Hills (Eagle Mountain area).

  - Beehive completed all fiber construction in Penrose, Thatcher, Elwood, Bear River, Howell, and Mantua, with administrative finalization pending.

- Ongoing Projects:

  - High Country, serving west of Herriman, has 66% of its fiber completed.

  - Centracom, working in central Utah (Kanosh Meadow, Leamington area), is 95% done with mainline fiber and is beginning drop installations.

  - NTUA (Navajo Nation) has completed pole preparation ("make-ready" work) and is awaiting right-of-way approvals, with progress expected by the end of the year.

  - Utah Broadband has started its project in West Mountain (outside Payson), with the first house recently hooked up. They aim to serve 1,000 locations in the area.

- Ribbon Splicing Ceremonies: Two ceremonies have been held to date (All West in Croydon and Direct Communications in White Hills), with five more planned.

4. Utah Broadband Center Federal Grants Update (Rebecca Dilg, Director, Utah Broadband Center, and Kenrick Gordon, Consultant, Witt O’Briens)

- Rebecca Dilg Utah provided an update on Federal Grants, specifically distinguishing them from the Broadband Access Grant previously discussed.

- Unserved and Underserved Locations: Based on the FCC's Broadband Data Collection (BDC) fabric 3.2 map, Utah has 43,500 homes and businesses lacking reliable broadband infrastructure.

- Broadband Definition: While the FCC's minimum is 25 Mbps download / 3 Mbps upload, grant programs now require at least 100 Mbps download / 20 Mbps upload to meet future needs and be eligible for funding. Fiber optics is considered the best technology for reliability, scalability, and gig speeds.

- Statewide Digital Connectivity Plan: This plan is mandated by Utah code 63 N. Dash 17. Dash 2 0, 1, which will be renumbered as of July 1 due to House Bill 542 moving the Utah Broadband Center from the Governor's Office of Economic Opportunity to the Utah Department of Transportation (UDOT).

  - The strategic plan aims to implement statewide broadband connectivity, promote digital equity, and apply for federal funds.

  - It involved submitting two plans (Digital Connectivity and Digital Access) to the National Telecommunications and Information Administration (NTIA) to secure BEAD funding. The Digital Access plan focuses on affordability, device access, and digital literacy.

- Funding Status:

  - Utah was allocated $317 million for infrastructure (BEAD) and $7.8 million for the Digital Equity Act.

  - The Digital Equity Act funding was cut and is no longer available as of May 9th, impacting programs and staffing.

  - Utah's BEAD funding is secure, but the grant program was changed. .

- BEAD Grant Process Changes (NTIA Policy Notice):

  - NTIA drastically revised its policy and procedures, with a new policy notice issued on June 6th. This requires the Utah Broadband Center to effectively restart its grant process.

  - Eliminated Requirements: Several regulatory requirements previously scored (e.g., labor employment, climate change, open access, net neutrality, local coordination, non-traditional providers, middle-class affordability plan) have been eliminated.

  - Low-Cost Service Options: Providers will now set their own low-cost service options, rather than the state.

  - Technology Neutrality: All technologies that can meet speed (100/20 Mbps), latency (under 100 ms), reliability, consistency, and scalability (including support for 5G, wireless successors, and advanced services) are now priority. While fiber optics is still seen as the most capable of meeting all these requirements, other technologies are not automatically deprioritized.

- Round 1 Application Results (now subject to revision/resubmission):

  - 846 total applications were received for 1461 UPFAs.

  - Fiber Applications: 396 fiber-eligible applications (meeting the 25% match requirement), with 210 non-duplicative. The average cost per broadband serviceable location (BSL) requested for fiber was $28,346, with a potential cap of $35,000 per location deemed reasonable by the state.

  - Non-Fiber Applications: 352 non-fiber proposals (fixed wireless, hybrid fiber coax, satellite), with 163 non-duplicative. The average BSL cost for non-fiber was $9,751.

  - Total BSLs Covered: Approximately 21,568 BSLs were included in the applications, roughly half of Utah's unserved/underserved locations.

- Rerunning the Grant Process:

  - Applicants can resubmit their previous applications (with eliminated scoring categories ignored) or submit revised applications, potentially removing high-cost BSLs or adjusting costs due to eliminated overhead.

  - New scoring will prioritize cost (minimal BEAD outlay and match). If competing proposals are within 15% of the lowest cost, additional weighting factors include speed to deployment, speed/technical capabilities of the network, and a bonus for previous preliminary/subgrantees.

5. Timeline for New BEAD Grant Round (Kenrick Gordon)

- The process is under a tight 90-day deadline.

- June 11th: Utah Broadband Center (UBC) posted a request for information from unlicensed fixed wireless providers to correct BSL data, with responses due June 25th.

- June 16th-23rd (7 days): Reopening of the pre-application round for new interested applicants.

- June 30th: Target date for UBC to submit a letter to NTIA confirming compliance with new rules and a corrected BSL list. NTIA approval expected by July 3rd.

- July 8th (10 days): New application period opens (closing July 17th).

- July 18th-27th (10 days): Completeness review and scoring (reduced from 2 weeks).

- Late July - Mid-August: Deconfliction and negotiation period, where UBC will work with applicants on overlapping BSLs and project adjustments.

- August 6th (Assumed): Special Award Condition (SAC) meeting with NTIA.

- August 18th (Assumed): Final proposal is planned to be ready for public comment.

- August 18th - September 1st (14 days): Public comment period (may be reduced by NTIA).

- September 4th: Final proposal submitted to NTIA.

6. Digital Access and Alternative Funding Sources (Lindsey Thurgood)

- Lindsey Thurgood emphasized the critical importance of digital access to ensure the full economic and social impact of the BEAD infrastructure investment.

- Key Areas of Impact: Digital equity addresses lack of Internet access, digital skills, and digital devices, disproportionately affecting rural communities, low-income households, and aging individuals.

- Economic Benefits of Digital Access:

  - Combining broadband access with digital access (devices, skills) can increase employment by 7-17%, potentially re-entering 7,600 to 18,500 Utahns into the workforce.

  - Low-income families could see an average increase of $147 per month or $2,200 annually from digital access, totaling an estimated $182 million in additional household income statewide for SNAP-eligible families.

  - Studies suggest a $2.40 societal return for every $1 invested in digital access.

- Impact of Digital Opportunity Grant Cut:

  - Before the funding cut, the Digital Opportunity Grant received 41 applications requesting over $14 million (exceeding the available $7.8 million).

  - Applications primarily focused on digital navigation (95%) and device distribution (70%), with significant benefits for rural communities (85%), low-income households (75%), and aging individuals (65%).

- Proposed Future Focus (Seeking State Funding):

  - UBC proposes continuing digital access initiatives with a focus on:

    - Community Coordination: Coordinating efforts among the ~350 existing digital opportunity providers in Utah to prevent duplication and maximize impact.

    - Digital Navigation Support: Training individuals in existing trusted agencies to become certified Digital Navigators, providing best practices without hiring many new staff.

    - Device Distribution: Creating a pipeline for state organizations, universities, and businesses to donate leased equipment for refurbishment and redistribution.

  - Funding Request: UBC is seeking state funds for two positions to support these initiatives throughout the BEAD program's tenure, as BEAD funds cannot be used for this purpose. The request will likely be made through UDOT and the Legislature.

7. Discussion on Future Meetings

- Reporting Structure Change: Due to the Utah Broadband Center moving to UDOT (effective July 1st), the statutory requirement for reporting to this advisory committee will change from quarterly to as needed. The UBC will now also report to the Utah Transportation Commission.

- Next Meeting Proposed: A meeting was proposed for August 13th, around 11:00 AM, to review the BEAD grant proposal before it is released for public comment. This date was chosen to avoid conflicts with upcoming events (like NCSL in early August) and allow the UBC team time to prepare the proposal.

8. Adjournment

- Representative Scott Chew called for a motion to adjourn the meeting.

- The meeting was adjourned by common consent.