Name of Committee: Community Development Committee

Meeting Date: 1/12/2026

Meeting Time: 5:00 PM

Meeting Location: Woodland Hills City Center + Remote Participants

Members Present:

- Kiersten Thomson (Committee Chair)

- Severin Johnson (Committee Member)

- Brandy John's (Committee Member)

- Carrie Malovich (City Council Liaison)

- Lori Thomas (Committee Member)

Other Attendees: Daniel Jensen

Members Excused: Chloe Cleveland

The meeting was called to order at __5:00 PM__ by __Kiersten Thomson__.

| Agenda Item | Approval of Minutes from June 23, 2025 Meeting |
| --- | --- |
| Discussion | The minutes from the last meeting on November 17, 2025, were circulated (2:18). After some discussion about locating the minutes (2:33). Later in the meeting, a motion to approve the minutes was made and seconded (40:48). The motion passed (40:55). |
| Motion | Lori Thomas |
| Second | Brandi Johns |
| Vote | Unanimous Vote to approve |

| Agenda Item | Discuss the Strategic Plan and Timeline |
| --- | --- |
| Discussion | The main agenda item was to discuss the plan for drafting and submitting the strategic plan to the planning commission and city council (3:04). The goal is to complete this within a three-month process (3:18) to avoid delays and manage the budget effectively (3:27). The strategic plan will serve as step-by-step goals to achieve the long-term objectives of the general plan (3:42). - Daniel Jensen shared examples from other Utah cities (4:28): - Payson City: Their strategic plan is an implementation matrix that turns general plan objectives into specific action items (5:00). Woodland Hills' general plan already includes these tiers, so it could serve as a strategic plan (5:27). - Washington City: Focused on big-picture visioning, emphasizing qualitative goals like maintaining a small-town feel, without specific action items (6:37). - Riverton City: A middle-ground approach, outlining vision, mission, core values, and then prioritizing 8-12 key focus areas from their general plan (7:30). Daniel believes this aligns best with Woodland Hills' needs (7:48). Daniel demonstrated an implementation matrix (8:36) created using AI (ChatGPT) (8:45). This matrix includes: - Goals, objectives, and action items (9:20). - Responsible parties (9:39). - Timelines (9:50). - Funding needs (10:03). - Key Performance Indicators (KPIs) (10:29). - This matrix would be more specific and could be a "living document" (11:01). Kari Malovich emphasized that the strategic plan should be a "living document" (12:45) to ensure short-term goals align with long-term general plan objectives (12:51). It should be revisited by the council regularly to ensure decisions align with the plan (16:27) and to identify areas for updates (13:31). The committee discussed whether to break down all general plan goals into micro-steps or focus on 6-12 key priorities (17:42). It was suggested that an implementation matrix (19:15) could be updated annually, allowing the council to check off completed items and add new ones (19:21). Designating a responsible party would ensure accountability (19:42). Addressing Draft General Plan Changes: The concern about strategizing based on a general plan draft that is still under review was raised (25:25). It was decided that major overarching goals are unlikely to change significantly, but intricate details might (25:41). Existing ongoing projects like the trail study (26:15) would already be incorporated. Next Steps for Strategic Plan Development: - Daniel will reach out to different committees and council members (27:02) for their five-year goals related to specific sections of the general plan (27:30). - Daniel will compile a draft of the strategic plan and an Excel file for the implementation matrix (28:34), with the Excel file being easily modifiable as a living document (29:03). A more polished version will be published on the website as an appendix to the general plan (32:48). - Daniel will take the lead in outlining potential actionable items and then seek feedback from committees (30:11). - The committee agreed that conversations with department heads and committees should start sooner rather than later (35:49). Next Meeting: The next meeting is scheduled for February 23rd at 5:00 PM (39:26) at City Hall (39:34). The goal for the next meeting is to review the input and framework of the strategic plan (39:43). Committee members are encouraged to review the draft and communicate via email in between meetings (40:09). |
| Motion | No vote was taken |
| Second |  |
| Vote |  |

Motion to Adjourn: Severin Johnson

Second: Lori Thomas

The meeting was adjourned at __5:41__p.m.

Kiersten Thomson

__________________________________________

Chair Secretary or Chairperson