Name of Committee: Community Development Committee

Meeting Date: 3/30/2026

Meeting Time: 5:00 PM

Meeting Location: Woodland Hills City Center + Remote Participants

Members Present: Kiersten Thomson, Lori Thomas, Brandi Johns, Severin Johnson (Arrival at 5:15 pm)

Other Attendees: Daniel Jensen, Sunrise Engineering; Kari Malkovich

Members Excused: Chloe Cleveland

The meeting was called to order at __5:00 PM__ by __Kiersten Thomson__.

| Agenda Item | Approval of Minutes from the 10/20/25 Meeting |
| --- | --- |
| Discussion | The committee approved the minutes from the January 12, 2026 meeting |
| Motion | Lori Thomas |
| Second | Brandi Johns |
| Vote | Unanimous Aye votes to approve |

| Agenda Item | General Plan Update |
| --- | --- |
| Discussion | - The committee discussed the status of the General Plan, noting that parts of the draft have been forwarded to the City Council after review by the Planning Commission (2:31-4:12). - Concerns were raised regarding the visibility of edits; the committee desires to see a side-by-side or color-coded comparison of the original committee draft versus the Planning Commission’s recommendations (4:42-5:23). |
| Motion | No vote was taken |
| Second |  |
| Vote |  |

| Agenda Item | Budget Update |
| --- | --- |
| Discussion | - Daniel reported that the project budget remains healthy. Out of the roughly $117,000 allocated to Sunrise Engineering, expenditures are in the low $80,000s, leaving sufficient funds to complete the remaining tasks (6:00-7:44). |
| Motion | No vote was taken |
| Second |  |
| Vote |  |

| Agenda Item | Strategic Plan Development |
| --- | --- |
| Discussion | - The strategic plan serves as a living document to support the General Plan with short-term, actionable goals (9:27-9:55). - Status: Daniel has been meeting with staff members. Ted provided action steps for Transportation, Water Preservation, Natural Environment, and Public Facilities (10:15-11:11). Progress on Parks and Trails is pending a response from the committee (11:13-11:28). - Format: The plan will remain an internal Excel-based spreadsheet for active tracking, while a simplified overview (1-2 pages) will be created for public access on the city website (32:31-36:34, 39:07-42:21). Action Items: Daniel will refine the document to include full terminology (no abbreviations), goal citations, and a color-coded, searchable table structure. |
| Motion | No vote was taken |
| Second |  |
| Vote |  |

The next community development committee meeting will be held on April 27, 2026 at 5:00 pm.

Motion to Adjourn: Lori Thomas

Second: Brandi Johns

Unanimous vote to adjourn.

The meeting was adjourned at __5:54__p.m.

Kiersten Thomson

__________________________________________

Chair Secretary or Chairperson