Loa Town & Waterworks

80 West Center ~ P.O. Box 183 ~ Loa, UT  84747

Phone 435.836.2160 ~ Fax 435.836.2266

Mayor – Cody Grundy, Town Clerk – Michelle Brian
Loa Town & Waterworks Council Meeting                                    May 14, 2020
Mayor Grundy opens the meeting. Bruce Brown is present, Bart Brian is present, Ryan Rees is present, Travis VanOrden is absent, Matt Morgan is present, & Michelle Brian is present. 
Business Items:
Arsenic: two months ago, arsenic blend was .96 and last month the blend was .96. The average for the quarter is still under .10. 
The board started with Sunrise first. They pulled out the maps for the water lines again and discussed all the options again and ways to curb the cost, but still fix what really needed attention. After a lengthy discussion about the water lines and needs, the town board came up with the best option for the town. They would be going for around 2.6 million rather than the 3.4 million that they originally planned. This change of plan would still upgrade the worst lines and be of the most benefit to the town now; but should keep the cost to the residents as low as they can. The list of improvements is as follows: Zone 1 – 8” and 10” lines on north end of town, Zone 2 – 8” lines on west and east main street, Zone 3 – 8” lines at southwest corner of town, replace meter setters, integrated system wide Scada system installed. The board has decided to do zone 1 and zone 2 and forgo the rest at this time unless they can do more with the 2.6 million, but they won’t know that until Sunrise revises the scope of work and pricing. Michelle will attach the documents for public view as well. 
The CIB application is due May 31st, Sunrise was planning on requesting a 50/50 grant loan at 1.5% for 30 years. According to the MAGI, the average culinary water rates should be $57.31. The town won’t know exactly where they stand until the summer months are over, but the rate scenario that Curt from Rural Water had made for them showed them to be in this area on average with the irrigation as well. The funding authorization would be October 2020 if they were given funding. Then the design and permit stage would happen between November 2020-February 2021. The bid phase would be February to March 2021. Then construction would be in the summer of 2021. This is all if CIB awards the town the grant/loan. If they do not, then the town will either go to the USDA or look at other avenues. 
Mayor asks for a motion to approve the project scope for design through the phases prior to funding from Sunrise Engineering. Ryan motions to approve the project scope proposal for design of the phases for the water project by Sunrise Engineering. Bart seconds the motion to approve the project scope proposal for design of the phases for the water project by Sunrise Engineering. All others vote in favor, motion carries. The project scope proposal by Sunrise Engineering is accepted. 
Mayor asks for motion to approve March minutes. Bart motions to accept the March minutes.  Bruce seconds the motion. All others vote in favor. Motion carries. Minutes for March are passed. No meeting was held in April due to Covid. 
Mayor asks for a motion to approve the May public hearing minutes. Ryan motions to approve the May public hearing minutes. Cody seconds the motion. All others vote in favor. Motion carries. Minutes for the May public hearing are passed. 

Mayor asks for a motion to approve the accounts payable for April and May. Bruce motions to approve the accounts payable for April and May. Ryan seconds the motion. All others vote in favor. Motion carries accounts payable for April and May are passed. 
Bank recs., standard financial reports, deposits, and delinquent water list are all approved by signature of all town board members. Michelle also has them make sure all the checks written match the reconciliation’s as well. 
Due to the length of business items, the town has opted to not do the newly elected officials training tonight. They will try to fit it in next month. 

Misc. item: Pace Ellett has a daughter and son in law that are wanting to build a home on his farm going to Fremont. He would like to hook up to the culinary line. The existing line is only a 2” line and the board doesn’t want to allow a home to be hooked onto a 2” line. They feel that all new developments must put in an 8” water line with hydrants so that they are compliant with code and upgrading the system. They would like to pass an ordinance stating that no meter hook ups will be allowed on any existing lines smaller than 4”. The upgrade to 8” lines must be paid for by the person wanting to hook up to the culinary line. Michelle will talk to Curt and see if he can help her write up an ordinance with that information. 

Information Items:
Michelle reminds the board of the budget hearing and adoption next month. They want her to check into road funds and see what they can use for them. They also want Matt to measure the worst areas and see what they are looking at. The mayor said the Ellis Brown is supposed to be getting him a cost for them as well. 
No other information was discussed.

The Mayor asks if anyone wants to make a motion to adjourn. Ryan makes a motion that they adjourn. Bart seconds it. All others vote in favor. Motion carries.   
Meeting Adjourned.
