MEMO:

June 14, 2021

To: Chair Chris Robinson

From: Ralph Becker

Re: Pillars Document/Statement Distribution and Meetings

With the completion and finalization of the CWC Pillars for a MTS by the CWC Board and the desire to send this to UDOT, State leadership, the media, and others, I’m providing for your consideration a suggested set of steps and meetings to get this information before the June 25 expected release date for the Draft LCC DEIS.

1. Send signed copy to UDOT - 6/14/2021 (Teri Newell, EIS Team)
2. Send to CWC Stakeholders Council 6/15/2021 - invite comments and discussion
3. Press Release to Media (6/21/2021)
4. Meetings with State Leadership (Governor, State Legislative Leadership) - week of 6/21
5. Send to Congressional Delegation and phone calls/meetings w/ Congressional Representatives - week of 6/21
6. Visits with Editorial Boards - week of 6/21 or 6/28

**Next Steps**

After release of the DEIS, the following steps are recommended during 45-day comment period:

1. Staff and jurisdictional review of DEIS (anticipated 6.25.2021)
2. Stakeholder Council discussion and input to CWC on DEIS (July 21, 2021 Stakeholders Council Meeting)
3. CWC Transportation Committee consideration of Comments on DEIS (meeting time TBD)
4. CWC Board consideration of Comments on DEIS (June 25-July 12; August 2nd 2021)
5. Action item on CWC Comments (CWC Board Meeting July 12, 2021)
6. Meetings with pertinent parties on CWC Comments on DEIS (if/when to be determined)
7. Deadline for public comment to UDOT LCC EIS Monday, August 9th 2021

We’ll be prepared to follow up on getting pertinent documents ready and setting up meetings upon your approval.

We should also discuss who should participate in any meetings.