Harvest Days Festival Committee						                July 14, 2022 
								City Hall Dahl Conference Room

MINUTES

1. Call to Order, Roll Call, Welcome
Chair Molly Signoretty called the meeting to order at 5:38 p.m. She also confirmed that a quorum was present.

	Molly Signoretty
	P

	George Ferris
	P

	Mike Williams
	A

	Rebecca Pipkin
	P

	P=Present    A=Absent



2. Agenda Review
No changes were made to the agenda.

3. Approve Minutes
By unanimous consensus the committee voted to approve the July 7, 2022 minutes.

4. New Business
a. Partner Updates
i. Unified Police Department
Not present this week, Committee Chair Signoretty will invite for next week to make sure that everything is set up for the festival. 
ii. Unified Fire Authority
EMT coverage for Friday night; six EMT will be available at the park on Saturday, especially monitoring for heat exhaustion; Brad Jewett, Emergency Manager for Midvale, will draft an Incident Action Plan and provide copies to the Committee.
b. Midvale City Department Updates
i. Administration – Budget review
1. Budget allowed for the event is $63,500, but we typically try and go under the budget so we can help pay for the upcoming year because of the way the fiscal year works. 
2. Big tent for audience to watch entertainment will cost about $9,000 – committee recommended getting this.
3. Five tents for carnival games – Event Planner Tonya Hoopes will look into renting/purchasing.
4. BINGO prizes- $1,961 – current cost; Online prizes were purchased, and additional items to purchase include:
a. Utah Warrior Rugby season tickets – $200 for 2 – switch out for the tablet as one of the grand prizes.
b. Firepit, is actually $250.
c. Gas card – from Sam’s club as a gift card.
d. Nintendo Switch Bundle – $350 from Costco.
e. Games to purchase – fishing for prizes, ring toss, duck match, knock down, and football toss.
f. Carnival Game prizes – will look for items from Oriental Trading Company and Amazon.
ii. Communications
1. Door Hangers – Committee Chair Signoretty will put on doors for people on the parade route.
2. Pre-inked stamps – for those who get a Bingo card.
3. Ordered flags for directions during the Festival.
4. Flyers – ordering 2000 to distribute, including in Spanish. 
c. Event Planner Update
i. Tents – $9000 for the large tent.
ii. Face painting – will be at the carnival area.
iii. Chalk artist will be at one of the booths.
d. Booth Vendors – no new applications.
e. Food Vendors
i. Skillets and Haole T’s have dropped out.
ii. Committee Member Williams and Committee Chair Signoretty will contact food trucks and check for availability; need about three more trucks.
f. Mayors Cup HORSE Basketball Tournament
i. Flyer is created and pre-registration is encouraged.
ii. Will be staffed/coordinated by volunteers.
iii. Boys and Girls Club is available if needed, providing three courts in total.
g. BINGO Planning
i. Midvale City Manager Matt Dahl will be a caller instead of Council Member Gettel. 
ii. Mayor Stevenson will call during the first and last 30 minutes of Bingo; Vice-Chair Ferris and Midvale City Manager Matt Dahl will call in between.
h. Volunteer Needs and Recruitment Updates
i. Reviewed volunteer spreadsheet to see the remaining needs. 
ii. Reviewed volunteer application and consent form – remove section asking for three references, change the question to “who referred you, how do you know about the event?”; remove employment verification.
iii. Orientation can be scheduled once we have contacts.
5. Harvest Days Festival Committee Member Comments
6. Adjournment
By consensus of the Harvest Days Festival Committee, the meeting was adjourned at 7:13pm.
