## A
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
A. Assessment of the Accord; Restatement and Recommitment of the Values and Principles from the Accord | Adopted on April 4, 2022 CWC Board Meeting: Resolution 2022-15 | Completed | Commitment by board, staff, and stakeholders to review bi-annually | Review at 2022 Retreat

## B
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
B. Assessment of the Accord; Specific Commitments and Negotiated Actions | Potential work plan item for 2022/2023 | Ongoing |  | Discussion topic for the 2022 Board Retreat
| Review matrix of action: 4.4.2022 CWC Board Meeting | Ongoing | link to deliverables matrix here -- Lindsey to update deliverables matrix -- Lindsey | Review the Mountain Accord Deliverables Matrix at 2022 Board Retreat
| Short term projects ongoing: to CWC Board May 2, 2022 | FY 21/22: 9 Projects funded FY 22/23: $50,000 Budgeted to begin work in Spring 2023 | Link to short term projects matrix here -- Lindsey https://cwc.utah.gov/projects/ | Potential to incorporate a match component of short-term project program; potential to increase funding; potential to diversify project sponsors and partner organizations
| Refine into Compact (delay work on a Central Wasatch Compact at this time). | On hold | Review minutes from Spring 2022 for discussion about Central Wasatch Compact -- Blake and Lindsey | Discussion topic for the 2022 Board Retreat

## C
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
C. Purpose of the Central Wasatch Commission | At the direction of the Board, staff develops the updated vision, mission, and purpose statement. | Ongoing |  | Discussion topic for the 2022 Board Retreat
| Provide a forum for cross-sectional and multi-jurisdictional to discuss and address issues in the Central Wasatch. | Ongoing |  | Central Wasatch Summit/Forum; similar to the Great Salt Lake Forum from Jan. 2022 -- "mini Mountain Accord/State of the Wasatch" -- Right before the 2023 legislative session -- fundraising opportunity for environmnetal dashboard?
| Engage the multiple jurisdictions (the State of Utah, Salt Lake County, U.S. Forest Service, etc.) in the solutions for the Central Wasatch Mountains as an objective for CWC actions. (What will work for each jurisdiction and what’s the forum for it?) | Ongoing | Forest Service joining as ex-officio Fall 2022
| The CWC is succeeding and accomplishing its designated purpose by providing the forum it was designed to achieve. The CWC measure for success or failure is not the degree to which generational, landscape-scale actions delineated in the Accord have been fully implemented. | Ongoing

## D
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
D. Governance Structure of the Central Wasatch Commission | The CWC should actively seek to improve involvement with the State of Utah, the U.S.Forest Service, Salt Lake County, and potentially other key governmental entities. The CWC should recruit and appoint state government formal relationships. | Ongoing | Create of matrix for State agency engagement and relationship status -- Blake | Forest Service joining as ex-officio Fall 2022 (Bekee? Lance? Dave?); CWC will cultivate a relationship with the newly hired canyon manager at SLCo
| Working with the Board, staff assigned to create a strategy for engaging with partner agencies, including regular communications with partners in the Central Wasatch Mountains. | Ongoing | Daily social media posts, weekly newsletter, regular communication with stakeholders and with Commissioners, regular communication with print and digital media, continual updating of web presence | Potential for Tiktok account; podcast; increased video web presence -- full time community engagement staff person?
| To continue the CWC structure, created by interlocal agreement, where the Commission is composed only of elected officials. There are non-elected, ex-officio representation. The CWC needs to settle on the way engagement occurs with the State of Utah and Salt Lake County. | Ongoing | Link matrix for State agency engagement -- Lindsey | Enage with SL County about being back on the Central Wasatch Commission; negotiate the State as an ex-officio member

## E
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
E. Scope of Discretion and Authority Granted to Staff and Future Staffing Levels | Staff to analyze issues, formulate recommendations and build consensus around issues for the Central Wasatch Mountains. | Ongoing
| Staff to implement the direction of the Board | Ongoing | Implementation of Strategic Plan, Mtn Accord Deliverables, and additional board direction | Further direction pending 2022 retreat and onoging EBAC/Board meetings
| Move forward with 2 FTE, under the new model | Completed | Adopted in FY22/23, Resolution 2022-29, 2022-30 | 6 month review Dec. 2022; consider adding additional FTE in 23/24

## F
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
Majority Voting, Weighted Voting and Consensus Support | Default standard of consensus with a mechanism to shift to a majority vote | Completed; Mechanism is a motion by two or three commissioners to have a majority vote rather than consensus | Adopted on April 4, 2022 CWC Board Meeting: Resolution 2022-15

## G
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
G. Frequency of Meetings | The CWC Board must meet in April, May, and June for transition planning and completing budget FY 22/23 | Completed
| Reminder audit must be received by board by end of September 2022 | Completed | Audit presented at Aug CWC meeting. No manegement letter | Begin housekeeping items for 22/23 audit
| Begin a bimonthly meeting schedule in the new fiscal year. (Aug., Oct., Dec. 2022) | Ongoing |  | Decide (Resolution) on 2023 schedule
| Executive, Budget, and Audit Committee (EBAC) meets monthly | Ongoing |  | Continue as is
| Continue Board retreat in Nov. (November 2022) | In progress | Begining planning process at July 2022 EBAC meeting, memo to EBAC 8/15 | Plan retreat for Nov. 2022

## H
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
H. CWC Representation and Engagement with External Entities | Annual presentations, or more frequently as circumstances may warrant, to the legislative bodies of CWC member jurisdictions. | Ongoing | Confirmed: Park City, Brighton, Alta, Sandy, Cottonwood Heights, Millcreek, Summit County Yet to confrim: SLC, Metro, UTA | Blake and Lindsey (and Chris) will tour the legislative bodies of member jurisdictions to present on the work and stauts of the CWC before the close of 2022 -- Lindsey to update presentation powerpoint
| Request regular formal presentation to CWC Commission meetings from the Forest Service, UDOT or other entities relevant to the ongoing work of the CWC. | Ongoing | FS presented at June 2022 Board meeting | UDOT scheduled for October 2022 meeting
| Chair and staff collaborate on who engages/participates in different meetings, events, and other interests. | In progress |  | Team meeting with Chris once every two weeks
| Staff develops a list of jurisdictions, various state departments, etc. on who to engage and level of interest | In progress | State matrix -- Blake
| Participating by formal invitation or informally in relevant boards and commissions | In progress | Develop rules and criteria | Talk with Chris about which boards would be appropriate

## I
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
I. CWC Funding | Ongoing member contributions | Approved budget FY22/23 | Address financial commitments of member jurisdictions | Pending discussion at September EBAC and 2022 Retreat
| Develop plan to pursue various funding sources | On going | A robust but non comprehensive list of potential funding sources is provided in the CGI report; review past work done around funding sources | Develop for retreat
| Look to partner with SHC members for 501c3 status | On hold pending further direction | Stakeholders Council agency members may offer their 501c3 status | Discussion topic for the 2022 Board Retreat
| If opportunity arises, CWC may still pursue a 501c3 subsidiary | On hold pending further direction | Pending further direction from CWC Board | Discussion topic for the 2022 Board Retreat
| Recommend the CWC continue to seek external funding to support short-term projects and other initiatives | Secured 2022 State Appropriations |  | See Funding Souces Matrix

## J
2022 Strategic Plan Topic | Task | Status | Notes | Future Action
J. Stakeholders Council Engagement | As part of the CWC 2022-23 implementation, budget will be provided for Stakeholder Council leadership training, and a clarification of the role of the Council. | Completed | $2,500 approved in budget FY22/23
| SHC will develop work plans, strategies, and committees at the April 20th 2022 meeting. | Completed | Link the April 20th meeting minutes -- Lindsey https://www.utah.gov/pmn/index.html
| Co-chairs will attend Executive Budget Audit Committee as ex-officio | Completed; Ongoing
| Standing agenda item on CWC board meeting for SHC updates and activities | Completed; Ongoing