CASTLE VALLEY SPECIAL SERVICE DISTRICT

REGULAR MEETING

DECEMBER 15, 2022

MEMBERS PRESENT                                                                                   STAFF PRESENT

| BRAD GILES LEONARD NORTON GARY PRICE | PAT SUNDSTROM JEFF TUTTLE DANNY VAN WAGONER JAMES WINN | JACOB SHARP THOMAS SITTERUD MERRIAL JOHANSEN DIANE HAGARA |
| --- | --- | --- |

MEMBERS NOT PRESENT

| TREVOR ROWLEY DAVID ROBERTSON | KENT WILSON PRESTON WILSON | CHRIS WINN |
| --- | --- | --- |

Welcome by Chairman, Brad Giles at 7:00pm.

1.	Discuss/Approve/Deny: Minutes of Thursday November 17, 2022

Motion was made by Danny Van Wagoner and seconded by Pat Sundstrom to approve the minutes of November 17, as prepared.  Motion carried by all present.

2.	Discuss/Approve/Deny: 2022 Construction Projects and Related Matters

a.	2022 Drainage Project

Jacob stated that Johansen Construction (JCI) is still working in Ferron.  They are finished laying the main line in and are now working on connections.  They’re trying to get done next week and will probably have to shut down after that.

Pay Estimate #4 is in the amount of $171,565.54 with $9,029.77 being held in retainage.  They are 66% complete and 89% on time used.

b.	2022 City Streets Project

Jacob reminded the board that we used Allred Construction as the contractor for the pond reconstruction in Emery.  He illustrated the work there stating that we received the liner and it was installed and completed; it is now full of water.  The materials ended up being $108,209.20, the installation was $38,555, the excavation and preparation was $167,016.20 for a grand total $313,780.40.

Jacob reminded the board that we received $191,691 from our 2019 project money to help complete this project.  This project is now complete.

Change Order #1 decreases the contract amount by $2,525.72, taking the final contract to $633,935.08.

Motion was made by Jeff Tuttle and seconded by Leonard Norton to approve Change Order #1 decreasing the amount of the contract by $2,525.72.  Motion carried by all those present.

Final Pay Estimate #7 is in the amount of $33,558.75.  This includes $31,598.75 being released from retainage.  They are 100% complete and 100% on time used.

3.	Manager’s Report

a.	Review Secondary Water Usage Reports

The board reviewed the secondary water usage reports.

4.	Discuss/Approve/Deny:  2022 Amended Budgets

The board reviewed the 2022 Amended Budgets.  He stated that negotiations were settled with the power company.  They ended settling on $3.7M total.  All entities have to pay by the end of the year.  The District’s portion is $512,108.00.  This is on the amended budget.  He reminded the board that we also paid a judgement levy earlier this year in the amount of $43,041.22.  The combined total is $555,149.22.

Jacob reminded the board that we overshot the road maintenance, pipes, valves and fittings and insurance.

Motion was made by Leonard Norton and seconded by Pat Sundstrom to approve the 2022 Amended Budgets.  Motion carried by all those present.

5.	Discuss/Approve/Deny:  2023 Final Budgets

The board reviewed the 2023 Final Budgets.

Motion was made by James Winn and seconded by Gary Price to approve the 2023 Final Budgets.  Motion carried by all those present.

6.	Discuss/Approve/Deny:  2023 Board Meeting Schedule

The board reviewed the 2023 Board Meeting Schedule, which is the third Thursday of each month at 7:00pm.

Motion was made by Pat Sundstrom and seconded by Leonard Norton to approve the 2023 Board Meeting Schedule.  Motion carried by roll call vote: Jeff Tuttle – yes; Danny Van Wagoner – yes; Leonard Norton – yes; Gary Price - yes; James Winn – yes; Pat Sundstrom – yes.

7.	Discuss/Approve/Deny:  2023 Holiday Schedule

The board reviewed the 2023 Holiday Schedule.

Jacob stated that the District usually gets a half day on Christmas eve, but because Christmas falls on a Monday in 2023, we didn’t put it on there.  He also stated that he did not put Juneteenth on there, but the employees have asked about it.

The board reviewed the holiday schedule and decided to add Juneteenth.

Motion was made by Gary Price and seconded by Danny Van Wagoner to approve the 2023 Holiday Schedule with amendment.  Motion carried by roll call vote: Jeff Tuttle – yes; Danny Van Wagoner – yes; Leonard Norton – yes; Gary Price - yes; James Winn – yes; Pat Sundstrom – yes.

8.	General Operational Items

Jacob thanked the board for their service and pointed them to the hoodies.

9.	Approval of Vouchers

Motion was made by James Winn and seconded by Leonard Norton to approve the vouchers.  Motion carried by roll call vote: Jeff Tuttle – yes; Danny Van Wagoner – yes; Leonard Norton – yes; Gary Price - yes; James Winn – yes; Pat Sundstrom – yes.

10.	Adjourn

Motion was made by Pat Sundstrom and seconded Gary Price to adjourn the meeting at 7:25pm.  Motion approved by all members present.